## JIRA (4)
Issue Type | Issue key | Summary | Assignee | Priority | Status | Created
Story | MUSE-525 | On impersonating Writer of Partner Community, creation of Article and Video fails. | amit.armarkar | High | Backlog | 2016-10-03 13:15
Bug | MUSE-523 | Navigation Cancelled error while creating an article | amit.armarkar | Low | Open | 2016-10-02 04:06
Bug | MUSE-518 | Info messages on each page should dynamically set its position | sanjay.ingle | Lowest | Open | 2016-09-19 02:49
Bug | MUSE-516 | Edge browser compatibility issue - Video review page observations on Muse | arpit.nagar | Medium | Open | 2016-09-16 10:22
Bug | MUSE-515 | Edge browser compatibility issue - Showing unwanted file extension for CC file upload | arpit.nagar | Lowest | Open | 2016-09-16 10:21
Story | MUSE-509 | Should not allow uploading Video of 3gp format | glenn | Low | Backlog | 2016-09-16 03:09
Story | MUSE-508 | EIC without video access permission is able to create video content | glenn | High | Backlog | 2016-09-15 16:27
Bug | MUSE-507 | Embedding video link in regular Article, shows Loading Video ... | sanjay.ingle | Medium | Open | 2016-09-15 15:18
Story | MUSE-505 | Editor is able to upload video "on behalf of" or "on top of" Creator | glenn | High | Backlog | 2016-09-15 14:40
Story | MUSE-500 | Facebook Share Cover Image for Video | glenn | High | In Progress | 2016-09-13 09:28
Story | MUSE-499 | Muse client side inactivity timeout is 50000 ms which is very short for Video Upload | glenn | Highest | Backlog | 2016-09-13 07:02
Story | MUSE-496 | Creators' contact info beside article for editors | vijay.diwakar | Medium | Backlog | 2016-09-13 05:40
Story | MUSE-476 | User is unable to cancel Encoding of video from Muse UI | sanjay.ingle | Low | Backlog | 2016-09-08 06:25
Bug | MUSE-471 | Azure server to store only 1 copy of video | sanjay.ingle | Medium | Open | 2016-09-06 07:00
Story | MUSE-447 | No option to delete selected Co-Author | sachin.kothe | Lowest | Backlog | 2016-09-04 07:48
Bug | MUSE-440 | Duplicate Slug (with space in between) is accepted for a new community. | amit.armarkar | Low | Open | 2016-09-02 15:45
Bug | MUSE-439 | Able to create two communities with same name | milind.deshpande | Medium | Open | 2016-09-02 15:45
Bug | MUSE-412 | Duration of video mm:ss doesn't show on cards | alex.lewis | Low | Open | 2016-08-19 11:15
Bug | MUSE-411 | Credits is below description/details instead of besides it | alex.lewis | Low | Open | 2016-08-19 11:12
Bug | MUSE-410 | Video right click option leads to JWPlayer site on the same Odyssey page | alex.lewis | Low | Open | 2016-08-19 11:07
Bug | MUSE-408 | Video play resolution doesn't show pixel rates for Auto | alex.lewis | Low | Open | 2016-08-19 09:24
Bug | MUSE-405 | Issue with resizing browser window | alex.lewis | Medium | Open | 2016-08-19 07:08
Bug | MUSE-404 | Issue with seeking at the middle of the video | alex.lewis | Medium | Open | 2016-08-19 07:06
Bug | MUSE-396 | Incorrect Resolution icon on iPad | alex.lewis | Medium | Open | 2016-08-18 09:00
Bug | MUSE-395 | Video gets paused on muting the video | alex.lewis | Medium | Open | 2016-08-18 08:49
Bug | MUSE-394 | Volume control and Resolution options get invible on video screen | alex.lewis | Medium | Open | 2016-08-18 08:44
Bug | MUSE-387 | No validation on Zip field | milind.deshpande | Lowest | Open | 2016-08-16 03:52
Bug | MUSE-386 | No validation on Email field | amit.armarkar | Lowest | Open | 2016-08-16 03:41
Story | MUSE-369 | Community Members - Should have provision to search members using Phone Number | vijay.diwakar | Medium | Backlog | 2016-08-12 04:29
Story | MUSE-365 | Provision for Content filtering by type of an article (Standard/Listicle/Video) and Community Name | glenn | Medium | Backlog | 2016-08-10 11:08
Bug | MUSE-362 | Communities Webpage is not mobile/tablet friendly | sachin.kothe | Low | Open | 2016-08-10 04:22
Bug | MUSE-361 | User can update slug for a community | amit.armarkar | Medium | Open | 2016-08-10 03:34
Bug | MUSE-360 | Duplicate email is accepted for a new community | amit.armarkar | Low | Open | 2016-08-10 03:29
Bug | MUSE-359 | Slug not available information stays on | amit.armarkar | Lowest | Open | 2016-08-10 03:26
Story | MUSE-103 | Slug field validations | glenn | Medium | Backlog | 2016-07-25 17:35
Story | MUSE-102 | (FF Browser) Password insecure console info | glenn | Medium | Backlog | 2016-07-25 17:20
Story | MUSE-101 | Unexpected error occurred while entering incorrect password | glenn | Medium | Backlog | 2016-07-25 17:13
Story | MUSE-100 | 'Complete Signup' button needs to be disabled while account creation backend process is running | glenn | Medium | Backlog | 2016-07-25 17:06
Story | MUSE-99 | (IE Browser) Popup to enter details is cutting in half (needs realignment) | glenn | Medium | Backlog | 2016-07-25 16:57
Story | MUSE-98 | No easy way to come out from in-between if first time user sign-in process isn't completed | glenn | Medium | Backlog | 2016-07-25 16:48
Story | MUSE-88 | No validation on phone number, email field of Writer application | glenn | Medium | Backlog | 2016-07-21 10:13